## Annex B
Annex B
Agency Name
Agency Address
Quarterly Report on Government Projects / Programs / Activities
For the Quarter ending MARCH 15, 2024
Agency/ Address | Projects/Programs/Activities Name | Location | Total Project Cost | Date Started | No. of Extensions | Target Completion Date | Project Status |  | Remarks
[7 empty] | % of Completion | Total Cost Incurred to Date
NAGUILIAN WATER DISTRICT | DRILLING OF A DEEPWELL WITH INSTALLATION OF EQUIPMENTS IN LIOAC NORTE PUMPING STATION | LIOAC NORTE, NAGUILIAN, LA UNION | 2677881.76 | - | N/A | - | 0% | - | NOTICE TO PROCEED DATED MARCH 15, 2024

## Annex B (2)
Annex B
Agency Name
Agency Address
Quarterly Report on Government Projects / Programs / Activities
For the ending APRIL 30, 2024
Agency/ Address | Projects/Programs/Activities Name | Location | Total Project Cost | Date Started | No. of Extensions | Target Completion Date | Project Status |  | Remarks
[7 empty] | % of Completion | Total Cost Incurred to Date
NAGUILIAN WATER DISTRICT | DRILLING OF A DEEPWELL WITH INSTALLATION OF EQUIPMENTS IN LIOAC NORTE PUMPING STATION | LIOAC NORTE, NAGUILIAN, LA UNION | 2677881.76 | MARCH 20, 2024 | N/A | JULY 18, 2024 | estimate 28% | - | ON - GOING RIMMING OF THE DRILLING FOLLOWED BY SCREENING